## Experiment Results
Epoch | Accuracy | Loss
5
20
50
100
Epsilon | Accuracy | Loss
0.1
1
50
100
epch 높ㄴ건 가능
AA GPU 부조ㅓㄱ
샘플링 사이즈 조절
안돌아갈시에 - 최상의 모델에서 테스팅을 할 수 없는게 리미테이션
FGSM Adversarial Attacks Confusion Matrix - Accuracy | [7 empty] | FGSM Adversarial Attacks Confusion Matrix - Accuracy
| Clean | Adversarial Attacks | [6 empty] | Clean | Adversarial Attacks
| (Eps 0.1, Epoch 10) | (Eps 0.1, Epoch 5) | (Eps 0.1, Epoch 10) | (Eps 0.5, Epoch 5) | (Eps 0.5, Epoch 10) | (Eps 1.0, Epoch 5) | (Eps 1.0, Epoch 10) |  | (Eps 0.1, Epoch 10) | (Eps 0.1, Epoch 5) | (Eps 0.1, Epoch 10) | (Eps 0.5, Epoch 5) | (Eps 0.5, Epoch 10) | (Eps 1.0, Epoch 5) | (Eps 1.0, Epoch 10)
Resting | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Resting | 1 | 1 | 1 | 1 | 1 | 1 | 1
Squat | 0.38 | 0.42 | 0.28 | 0.11 | 0.17 | 0.12 | 0.24 | Squat | 0.38 | 0.42 | 0.28 | 0.11 | 0.17 | 0.12 | 0.24
Stepper | 0.5 | 0.33 | 0.27 | 0.33 | 0.43 | 0.36 | 0.34 | Stepper | 0.5 | 0.33 | 0.27 | 0.33 | 0.43 | 0.36 | 0.34
Clean (Train 100 epoch, Test 10 epoch, Epsilon 0.1)
Adversarial Attacks (Test 5 epoch, Epsilon 0.5) |  |  |  | Adversarial Attacks (Test Epoch 10, Epsilon 0.5)
test epoch 5 // eps 1.0 |  |  |  | test epoch 10 // eps 1.0
test epoch 5 // eps: 0.1 |  |  |  | tesh epoch 10 // eps 0.1

## Artefact Development
Table 3. Core IT Artefacts Studeid
Core IT Artefact
Hardware | Macbook Air M2 with 8GB memory
Operation and system software

## Project Management
[8 empty] | SIT723 | [16 empty] | SIT724
[8 empty] | 2022-11-14 |  |  |  | 2022-12-12 |  |  |  | 2023-01-09 |  |  |  |  | 2023-02-13 |  |  |  | 2023-03-13 |  |  |  | 2023-04-10 |  |  |  | 2023-05-08 |  |  |  |  | 2023-04-10
| Project Start Date: |  | 2022-11-21 |  |  |  |  | 2022-11-14 |  |  |  | 2022-12-12 |  |  |  | 2023-01-09 |  |  |  |  | 2023-02-13 |  |  |  | 2023-03-13 |  |  |  | 2023-04-10 |  |  |  | 2023-05-08 |  |  |  |  | 2023-06-05
| Project Name: Thesis Research Project A | [5 empty] | Week starting: | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19
# | Activity | Assigned To | Start | End | Days | Status | % Done
1 | Research Project Introduction | Chris Kim | 2022-11-09 | 2022-11-21 | 9 | Complete | 100% | bar: 2022-11-21
2 | Research Project Allocation | Chris Kim | 2022-11-09 | 2022-11-21 | 9 | Complete | 100% | bar: 2022-11-21
3 | Research Project Initiation | Chris Kim | 2022-11-21 | 2022-12-05 | 11 | Complete | 100% | bar: 2022-12-05
4 | Research Project Planning | Chris Kim | 2022-11-21 | 2022-12-12 | 16 | In Progress | 90% | bar: 2022-12-12
5 | Literature Review | Chris Kim | 2022-12-05 | 2023-02-07 | 47 | Complete | 100% | bar: 2023-02-06
6 | Design Research Questions | Chris Kim | 2022-12-24 | 2023-01-29 | 25 | In Progress | 60% | bar: 2023-01-23
7 | Design Research Artefacts | Chris Kim | 2023-01-09 | 2023-02-13 | 26 | In Progress | 100% | bar: 2023-02-13
8 | Design Research Artefacts - Future Work | Chris Kim | 2023-03-06 | 2023-06-19 | 76 | Blocked | 5% | bar: 2023-06-19
9 | Execute Experiments | Chris Kim | 2023-01-09 | 2023-02-13 | 26 | Complete | 70% | bar: 2023-02-13
10 | Evaluate Results | Chris Kim | 2023-01-30 | 2023-02-13 | 11 | Complete | 85% | bar: 2023-02-13
11 | Thesis Writing | Chris Kim | 2023-01-30 | 2023-02-24 | 20 | Complete | 100% | bar: 2023-02-20
12 | Establish Future Studies | Chris Kim | 2023-03-06 | 2023-06-19 | 76 | Not Started | 30% | bar: 2023-06-19
14 | Project Closure SIT723 | Chris Kim | 2022-11-21 | 2023-02-24 | 70 | Complete | 100% | bar: 2023-02-20
FALSE
TRUE
Statuses |  | TRUE
Not Started |  | FALSE
In Progress |  | FALSE
Blocked
Complete
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))
End = [Start]+14

## Risk Management
Risk | Magnitude | Risk management plan
Sample data size | Low-Medium | For future experiment, the use of MIMIC III data will solve the sample size issue with the dataset
Adversarial Attack types | Medium-high | In future study, data modification, model modification and auxiliary tools will be considered as a soure of adversarial attacks.
Simple RNN Model | Medium | For this study, only a simple RNN model is used. However, for the future study which will carry out in T1 2023, a more complex CNN model is considered

## Physiological Signal
Common Signal | Keywords | No. Publications since 2016 (as of 23 Feb 2023)
Electro-encephalogram | EEG, Electroencephalogram, Electroencephalography | 54100
Electrocorticogram | ECG, EKG, Electrocardiogram | 48900
Electromyogram | EMG, Electromyogram | 22100
Electrocorticogram | ECoG, Electrocorticogram, Electrocorticography | 15400
Electrococulogram | EOG, Electroculogram | 2800
Electrodermal Activity | EDA, GSR, EDR, Electrodermal, Galvanic Skin Response | 15300
Photoplethysmogram | PPG, Photoplethysmogram, Photoplethysmography | 7650
Heart Rate Variability | HRV, Heart Rate Variability | 18300
Blood Pressure | Blood pressure | 378000
Oxygen Saturation | SpO2, Oxygen Saturation, Blood Oxygen | 69400
Pulse Rate | Pulse Rate | 128000
Respiration | Respiration | 95300
Skin Temperature | Skin Temperature | 163000
Eye Movement | Eye movement | 101000
Common Signal | Keywords | No. Publications since 2016 (as of 23 Feb 2023)
Electro-encephalogram | EEG, Electroencephalogram, Electroencephalography | 54100
Electrocorticogram | ECG, EKG, Electrocardiogram | 48900
Electromyogram | EMG, Electromyogram | 22100
Electrocorticogram | ECoG, Electrocorticogram, Electrocorticography | 15400
Electrococulogram | EOG, Electroculogram | 2800
Electrodermal Activity | EDA, GSR, EDR, Electrodermal, Galvanic Skin Response | 15300
Photoplethysmogram | PPG, Photoplethysmogram, Photoplethysmography | 7650
Heart Rate Variability | HRV, Heart Rate Variability | 18300
Blood Pressure | Blood pressure | 378000
Oxygen Saturation | SpO2, Oxygen Saturation, Blood Oxygen | 69400
Pulse Rate | Pulse Rate | 128000
Respiration | Respiration | 95300
Skin Temperature | Skin Temperature | 163000
Eye Movement | Eye movement | 101000

## Defences
Defences | Examples | Refs
Data Modification | adversarial training, data compression, data randomisation, transferability blocking, gradient hiding and many more
Model Modification | regularisation, defensive distilliation, feature squeezing, and a mask layer
Auxiliary Tools | adversarial detection models, defence-generative adversarial nets (defence-GAN), high-level representation guided denoiser and so on

## Deliverables
Activity | Description | Date
Iteration 1 | T3 2022
Design | Design and develop a Research model

## Milestones
Artefact | Description | Date
Design | Google Colaboratory Document | 2023-02-13
Results of Prototype 1 | Working Prototype 1 Iteration 1 and 2 | 2023-02-13

## Reference used
Cardiovascular disease | World Health Organization, Cardiovascular diseases, WHO, n.d. | https://www.who.int/health-topics/cardiovascular-diseases#tab=tab_1
https://arxiv.org/pdf/1811.12026.pdf
Attacks on State-of-the-Art Face Recognition using Attentional Adversarial Attack Generative Network